## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Data Analytics
INTERN NAME: | Narendra Patil
PROJECT NAME: | Student Success Metrics: A Comprehensive Data Analysis
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2024-08-17
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Student Success Metrics: A Comprehensive Data Analysis
PROJECT ID
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2024-06-25 | Error in loading the Excel file into pandas DataFrame | Technical Issue | No | Ensure all necessary libraries are installed before data loading | Installed a missing library to read Excel files (openpyxl or xlrd) | Narendra Patil | SOLVED | -
2 | 2024-07-02 | Duplicated entries in College Names | Data Quality | No | Validate and clean data early in the process to avoid inconsistencies | Checked unique entries, standardized the names | Narendra Patil | SOLVED | -
3 | 2024-07-03 | Multiple entries in single column "How did you get to know about the event" | Data Format | No | Ensure uniform entry format by applying a single standardized value | Selected the first entry from multiple entries in the column | Narendra Patil | SOLVED | -
4 | 2024-07-06 | Students with the same name but different colleges | Data Integrity | No | Always use composite keys when dealing with potential duplicate entries | Created a composite key using student name and college name | Narendra Patil | SOLVED | -
5 | 2024-07-19 | Inconclusive correlation graph due to categorical nature of columns | Visualization | No | Choose appropriate visualizations based on data type | Used a box plot to display relationships between categorical and numerical attributes | Narendra Patil | SOLVED | -