## RAID LOG
RAID Log
| Project title: | Student Success Metrics: A Comprehensive Data Analysis |  | Project Id: |  | Project Manager: | Harshada Topale
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2024-09-10 | Project Team Lead: | Suraj Mane
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Incomplete or inaccurate data could impact analysis results | Incorrect data may lead to misleading insights and erroneous conclusions, causing rework and delays in project delivery. | Implement a thorough data validation process before analysis, and use tools to identify missing values or outliers. | Data Analyst Intern | Critical |  | Closed | Risk
2 | Risk | Potential difficulties in handling and processing large datasets. | Handling large datasets may result in slow processing times, memory issues, or incomplete results, affecting timelines. | Break the dataset into smaller manageable chunks, and use efficient data processing libraries like Dask or parallel processing. | Data Engineer | High |  | Closed | Assumption
3 | Risk | Misalignment of expectations regarding the depth and scope of the analysis. | Failure to meet stakeholder expectations could lead to dissatisfaction or requests for rework, delaying project completion. | Ensure regular communication with stakeholders, set clear deliverables, and manage expectations throughout the project. | Project Manager | High |  | Closed | Issue
4 | Assumption | The dataset provided is comprehensive and accurate, with no outlier effects. | If the dataset is incomplete or has significant outliers, additional cleaning and preprocessing will be required, leading to delays. | Verify dataset quality early, run outlier detection techniques, and inform stakeholders if assumptions are violated. | Data Analyst Intern | Moderate |  | Closed | Dependency
5 | Assumption | Stakeholders are available for regular reviews and feedback. | Lack of timely feedback may result in misaligned deliverables and delays. | Schedule regular review meetings with stakeholders and agree on key milestones and feedback points. | Project Manager | Moderate |  | Closed
6 | Assumption | Necessary tools and resources (e.g., Python libraries, software) are accessible throughout the project. | Lack of access to required tools could halt progress, impacting project timelines. | Ensure all necessary tools and software are installed and available to all team members before the project begins. | Tech Lead | Low |  | Closed | Open
7 | Issue | Inconsistent data format | Leads to difficulties in cleaning and analysis, causing potential delays in the project timeline. | Apply data transformation techniques to standardize formats, or create a script for automatic correction. | Data Engineer | High |  | Closed | Closed
8 | Issue | Duplicated data entries | Causes skewed analysis and incorrect results. May lead to additional data cleaning time. | Implement deduplication strategies during the data cleaning phase, and use checks to identify duplicates early. | Data Analyst Intern | Moderate |  | Closed
9 | Dependency | Limited to personal capacity and Python tools. | A lack of resources or capacity may slow down the project and delay deliverables. | Prioritize tasks, allocate time effectively, and make use of automated tools to reduce manual workload. | Project Manager | Moderate |  | Closed | Critical
10 | Dependency | Exclusively using Python for all stages of the project. | If Python tools or libraries encounter limitations, the project could face delays or the need for retooling. | Pre-validate Python tools for all required tasks and identify any limitations early. | Tech Lead | Moderate |  | Closed | High
11 | Dependency | Dependent on source data (cannot get new data or updated data). | If the provided data is insufficient or outdated, it will directly affect the quality of the analysis. | Communicate with stakeholders to ensure the source data is complete and relevant, and establish backup data sources if possible. | Project Team Lead | Critical |  | Closed | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24