## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
IAC Internship Program 2023 - Data Analytics Project Schedule
|  | PROJECT START DATE | 2024-06-11
|  | Display Week Sr No | 1 | [11 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08 | [6 empty] | 2024-07-15 | [6 empty] | 2024-07-22 | [6 empty] | 2024-07-29 | [6 empty] | 2024-08-05
 | time axis 2024-06-10 to 2024-08-11
Sr No | Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | [63 empty] | S | time axis 2024-06-10 to 2024-08-11
1 | Initiation
1.1 |  | Creating Project charter |  |  |  | Narendra Patil | 2024-06-11 | 2024-06-14 | 2024-06-14 | 5 | Completed | completed
1.2 |  | Requirment Gatherning |  |  |  | Narendra Patil | 2024-06-11 | 2024-06-16 | 2024-06-16 | 5 | Completed | completed
2 | Planning
2.1 |  | Creating SRS Document |  |  |  | Narendra Patil | 2024-06-14 | 2024-06-16 | 2024-06-20 | 5 | Completed | completed
2.2 |  | Creating WBS Document |  |  |  | Narendra Patil | 2024-06-14 | 2024-06-16 | 2024-06-21 | 5 | Completed | completed
2.3 |  | Creating RAID logs |  |  |  | Narendra Patil | 2024-06-14 | 2024-06-16 | 2024-06-22 | 5 | Completed | completed
2.4 |  | creating Project Schedule |  |  |  | Narendra Patil | 2024-06-14 | 2024-06-16 | 2024-06-23 | 5 | Completed | completed
3 | Development
3.1 |  | Initial Study of Data |  |  |  | Narendra Patil | 2024-06-16 | 2024-06-30 | 2024-06-25 | 5 | Completed | completed
3.2 |  | Data Cleaning |  |  |  | Narendra Patil | 2024-06-16 | 2024-06-30 | 2024-06-30 | 5 | Completed | completed
3.3 |  | Data Manipulation |  |  |  | Narendra Patil | 2024-06-16 | 2024-06-30 | 2024-07-01 | 5 | Completed | completed
3.4 |  | Data Transformation |  |  |  | Narendra Patil | 2024-06-16 | 2024-06-30 | 2024-07-02 | 5 | Completed | completed
3.5 |  | Exploratory Data Analysis |  |  |  | Narendra Patil | 2024-06-16 | 2024-06-30 | 2024-07-10 | 5 | Completed | completed
3.6 |  | Data Visualizations |  |  |  | Narendra Patil | 2024-06-16 | 2024-06-30 | 2024-07-10 | 5 | Completed | completed
3.7 |  | Data Analysis |  |  |  | Narendra Patil | 2024-06-16 | 2024-06-30 | 2024-07-10 | 5 | Completed | completed
3.8 |  | Generating Insights |  |  |  | Narendra Patil | 2024-06-16 | 2024-06-30 | 2024-07-15 | 5 | Completed | Completed
4 | Documentation
4.1 |  | project report |  |  |  | Narendra Patil | 2024-07-15 | 2024-07-25 | 2024-07-30 | 10 | Completed | Completed
4.1 |  | explaination video |  |  |  | Narendra Patil | 2024-07-25 | 2024-08-05 | 2024-08-15 | 10 | Completed | Completed
4.1 |  | lesson learnt |  |  |  | Narendra Patil | 2024-08-05 | 2024-08-10 | 2024-08-20 | 10 | Completed | Completed
4.1 |  | closure and submission |  |  |  | Narendra Patil | 2024-09-10 | 2024-09-10 | 2024-09-10 | 1 | Completed | Completed
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you